## Detailplan
[6 empty] | PW1 | PW2 | PW3 | PW4 | PW5 | PW6 | PW7 | PW8 | PW9 | PW10 | PW11 | PW12 | PW13 | PW14 | PW15 | PW16 | PW17 | PW18 | PW19 | PW20
[6 empty] | KW38 | KW39 | KW40 | KW41 | KW42 | KW43 | KW44 | KW45 | KW46 | KW47 | KW48 | KW49 | KW50 | KW51 | KW52 | KW1 | KW2 | KW3 | KW4 | KW5
Nr |  |  | Task | Progress | State | 16.09. - 22.09. | 23.09. - 29.09. | 30.09. - 06.10. | 07.10. - 13.10. | 14.10. - 20.10. | 21.10. - 27.10. | 28.10. - 03.11. | 04.11. - 10.11. | 11.11. - 17.11. | 18.11. - 24.11. | 25.11. - 01.12. | 02.12. - 08.12. | 09.12. - 15.12. | 16.12. - 22.12. | 23.12. - 29.12. | 30.12. - 05.01. | 06.01. - 12.01. | 13.01. - 19.01. | 20.01. - 26.01. | 27.01. - 02.02.
1 |  |  | Analyse-Phase | 73.3333 | Not started
| 1.1 |  | Auftragsinterpretation erstellen | 100 | In progress
| 1.2 |  | Terminplanung erstellen | 80 | In progress
| 1.3 |  | Situationsanalyse durchführen | 90 | In progress
| 1.4 |  | System- und Kontextgrenze definieren | 90 | In progress
| 1.5 |  | Projektanforderungen definieren | 80 | In progress
| 1.6 |  | Meilenstein: Review der Projektanforderungen | 0 | Not started
2 |  |  | Planungs-Phase | 0 | Not started
| 2.1 |  | Definieren der Arbeitspakete | 0 | Not started
| 2.2 |  | Definieren der Systemarchitektur | 0 | Not started
| 2.3 |  | Erstellen des Gate-Plans | 0 | Not started
| 2.4 |  | Meilenstein: Review des Gate-Planes | 0 | Not started
3 |  |  | Umsetzungs-Phase | 0 | Not started
| 3.1 |  | Arbeitspaket 1: | 0 | Not started
|  | 3.1.1. |  | 0 | Not started
|  | 3.1.2. |  | 0 | Not started
| 3.2 |  | Arbeitspaket 2: | 0 | Not started
|  | 3.2.1. |  | 0 | Not started
|  | 3.2.2. |  | 0 | Not started
| 3.3 |  |  | 0 | Not started
| 3.4 |  |  | 0 | Not started
| 3.5 |  |  | 0 | Not started
| 3.6 |  | Meilenstein: | 0 | Not started
4 |  |  | Auswertungs-Phase | 0 | Not started
| 4.1 |  | Auswertung des aktuellen Standes | 0 | Not started
| 4.2 |  | Vergleich mit Anforderungen | 0 | Not started
| 4.3 |  | Weiterführende Arbeiten definieren | 0 | Not started
5 |  |  | Sonstiges | 0 | Not started
| 5.1 |  | Thesisstart | 0 | Not started
| 5.2 |  | Zwischenpräsentation | 0 | Not started
| 5.3 |  | Bookeintrag | 0 | Not started
| 5.4 |  | Projektende | 0 | Not started
| 5.5 |  | Präsenation der Arbeit | 0 | Not started

## Status
Not started
In progress
On hold
completed

## Grobplan
| PW1 | PW2 | PW3 | PW4 | PW5 | PW6 | PW7 | PW8 | PW9 | PW10 | PW11 | PW12 | PW13 | PW14 | PW15 | PW16 | PW17 | PW18 | PW19 | PW20
| KW38 | KW39 | KW40 | KW41 | KW42 | KW43 | KW44 | KW45 | KW46 | KW47 | KW48 | KW49 | KW50 | KW51 | KW52 | KW1 | KW2 | KW3 | KW4 | KW5
Analyse-Phase | bar: PW1 KW38 to PW2 KW39
Planungs-Phase | bar: PW3 KW40
Umsetzungs-Phase | bar: PW4 KW41 to PW14 KW51; PW17 KW2
Auswertungs-Phase | bar: PW18 KW3